## Sheet1
Famiy |  | Sp 23 | Su 23 | Au 23 | Sp 24 | Su 24 | Au 24 | Sp 25 | Su 25 | Au 25 | Sp 26 | Su 26 | Au 26 | Sp 27 | Su 27 | Au 27 | Sp 28 | Su 28 | Au 28 | Sp 29 | Su 29 | Au 29 | Sp 30 | Su 30 | Au 30
St Michael's | 1 | Join
Family 1 | 3 |  |  | Join
Family 2 | 6 | Start |  |  |  | Join
Fam 3 - Bolton South | 5 |  | Start |  |  |  | Join
Fam 4 - Rochdale | 5 |  |  | Start |  |  |  | Join
Fam 5 - Bury & Salf | 5 | [6 empty] | Start |  |  | Join
Fam 6 - Salford | 7 | [9 empty] | Start |  | Join
Fam 7 - Roch/Midd | 5 | [10 empty] | Start |  |  | Join
Fam 8 - Bolton West | 6 | [11 empty] | Start |  |  |  | Join
Fam 9 - Salford | 7 | [13 empty] | Start |  |  |  | Join
Fam 10 - Bolton | 6 | [15 empty] | Start |  |  |  | Join
Family 11 - Salford | 6 | [20 empty] | Start |  |  | Join
|  | Stage 1 & 2 consent window | [6 empty] | DfE approval and project window | [7 empty] | Conversion date window
St Michael's (1) | St Michael's
Family 1 (2) | St Cuthbert's (Rochdale), St Ethelbert's (Bolton) , St Joseph's and St Bede's (Bury)
Family 2 (5) | St Joseph's (Ram), St Bernadette's (WhiteField), St Mary's (Rad), Our Lady of Grace (Prestwich) St Joseph's (Heyw)
Fam 3 - Bolton S/Salford (5) | OLOL, St Peter & Paul, St Teresa's, Mount St Joseph, St Teresa's Irlam
Fam 4 - Rochdale (5) | Holy Family (Kirkholt), Sacred Heart, St John's, St Mary's (Littleborough), St Vincent's, Holy Family RC/CE (TBC)
Fam 5 - Bury & Salf (5) | Guardian Angels, Our Lady of Lourdes, Holly Mount, St Marie's, St Philips (Salford)
Fam 6 - Salford (7) | St Ambrose Barlow, St Mark's, St Charles, St Luke's, St Mary's, Christ the King, St Edmunds
Fam 7 - Roch/Midd (5) | St Gabriel's, St Peter's, St ThomasMore, St John Fisher, Cardinal Langley
Fam 8 - Bolton W (6) | St Bernard's, St Mary's, Sacred Heart, Holy Family, Our Lady's, St Joseph's, St William of York
Fam 9 - Salford (7) | St Boniface, St Thomas of Canterbury,Holy Family, St Joseph's, St Sebastian's, Cathedral Sch of St Peter and St John, All Hallows
Fam 10 - Bolton (6) | Holy Infant & St Anthony, Ss Osmund & Andrew, St Brendan's, St Columba's, St John the Evangelist, St Joseph's, St Thomas of Canterbury
Family 11 - Salford (6) | Holy Cross and All Saints, St Glbert's, St Joseph the Worker, St Mary's, St Patrick's